## Sheet1
行标签 | 计数项:Number | PM_2020 | Opend | In Progress | Closed | Total
2017年 | 23 | Jan | 8 | 5 | 4 | 17
2018年 | 207 | Feb | 3 | 7 | 3 | 13
2019年 | 192 | Mar | 13 | 15 | 8 | 36
2020年 | 52 | Apr | 11 | 18 | 19 | 48
1月 |  | May | 9 | 6 | 10 | 25 | PM_2020 | Opend | Completed
Cancelled | 1 | [5 empty] | Jan | 6 | 1
Closed | 7 | [5 empty] | Feb | 0 | 1
1月 汇总 | 8 | [5 empty] | Mar | 4 | 1
2月 | [6 empty] | Apr | 1 | 0
Closed | 3 | [5 empty] | May | 2 | 2
2月 汇总 | 3
3月
Cancelled | 1
Closed | 11
Pending | 1
3月 汇总 | 13
4月
Cancelled | 1
Closed | 9
Pending | 1
4月 汇总 | 11 | PM_2019 | Opend | In Progress | Closed | Total
5月 |  | Jan | 36 | 30 | 20 | 86
Assigned | 2 | Feb | 12 | 12 | 20 | 44
Cancelled | 1 | Mar | 21 | 5 | 28 | 54
Closed | 5 | Apr | 20 | 10 | 21 | 51
In progress | 1 | May | 17 | 10 | 17 | 44
5月 汇总 | 9
6月
Assigned | 2
Closed | 2
In progress | 4
6月 汇总 | 8
总计 | 474

## Page 1
Number | State | Assignment group | Priority | Short description | Assigned to | Created
PTASK0069150 | Pending | AMS-AMO App Support Team-CN | 4 | MTS系统光大外点的 我的工单-工单处理的点击【拨打】按钮 提示："AreaCode未定义" | zhang Haibo | 2020-04-27 11:10
PTASK0067228 | Pending | AMS-AMO App Support Team-CN | 4 | 华夏项目外点mts，因网络断线导致正在分配CallList数据被锁，无法重新下发。 | zhang Haibo | 2020-03-09 17:22
PTASK0070941 | Assigned | AMS-AMO App Support Team-CN | 4 | 37E000000041 客户李萦萦 (客户号：03150512)，3.15号投保AGY一年期以上产品，影像居住地址与联系地址均正常有地址门牌号，3.28投保TM一年期产品，家庭地址为广东省深圳市无地址门牌号，目前客户层地址为无门牌号地址，请协查系统逻辑并尽快回复 | zhang Haibo | 2020-06-09 11:17
PTASK0069603 | Assigned | AMS-AMO App Support Team-CN | 4 | 质检=>质检任务创建(指定保单)页面，根据导入保单生成质检任务功能中，校验保单TSR是否为黑名单时，程序有缺陷；导致将TSR是黑名的保单，生成的质检任务为非黑名单任务。 | zhang Haibo | 2020-05-08 15:05
PTASK0070899 | Assigned | AMS-AMO App Support Team-CN | 4 | 该单自动发送核心LA时，未收到LA返回的报文，导致未能将受理信息回写到保单信息中。 | zhang Haibo | 2020-06-08 15:59
PTASK0069940 | Assigned | AMS-AMO App Support Team-CN | 4 | MTS系统的233002655431、保单号05068778 出现重复数据 | zhang Haibo | 2020-05-15 16:57
PTASK0071002 | In progress | AMS-AMO App Support Team-CN | 4 | 投保单号与设备ID不能为空，阻断影像加签流程 | lan Lan | 2020-06-10 11:27
PTASK0071062 | In progress | AMS-AMO App Support Team-CN | 4 | 生存金领取的查询被保人信息的时候缺少条件 | zhang Song | 2020-06-11 10:44
PTASK0071003 | In progress | AMS-AMO App Support Team-CN | 4 | 未拆分报表中的渠道拆分, 之前有"branchtype=5"的没有做渠道更新，导致报表中渠道分类错误，需要修正报表逻辑 | Junhao Hu | 2020-06-10 11:33
PTASK0071060 | In progress | AMS-AMO App Support Team-CN | 4 | 保全变更确认书影像无签字问题 | lan Lan | 2020-06-11 10:11
PTASK0070190 | In progress | AMS-AMO App Support Team-CN | 4 | imap2.0 保单影像件pdf显示为缩小版问题 | lan Lan | 2020-05-21 15:11
PTASK0043453 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-08-02 15:04
PTASK0044737 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-09-06 15:07
PTASK0040624 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-05-22 17:04
PTASK0037039 | Closed | AMS-AMO App Support Team-CN | 3 | Identify Root Cause | Li Chen | 2018-03-28 11:29
PTASK0049867 | Closed | AMS-AMO App Support Team-CN | 4 | 系统内满期金到期前提醒报表数据无法刷出，提示没有可用数据，请核实反馈，谢谢 | Porter Deng | 2019-01-09 11:03
PTASK0047398 | Closed | AMS-AMO App Support Team-CN | 4 | ODS 模型超时 | Shutao Luo | 2018-11-07 10:57
PTASK0063520 | Closed | AMS-AMO App Support Team-CN | 4 | 转换4位码为精算码并增加三个字段的推送 | Shutao Luo | 2019-12-06 19:42
PTASK0036022 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-03-14 15:56
PTASK0055432 | Closed | AMS-AMO App Support Team-CN | 4 | 单证加签空白优化 | lan Lan | 2019-05-31 17:39
PTASK0067144 | Closed | AMS-AMO App Support Team-CN | 4 | ODS模型表LCCONTAD的MD5拼接有问题，导致数据未更新 | Porter Deng | 2020-03-06 11:14
PTASK0063007 | Closed | AMS-AMO App Support Team-CN | 4 | 光大项目外点MTS系统的任务分配 ，无法分配提示："非本任务分配记录的分配人，不能修改本任务分配" 问题 | zhang Haibo | 2019-11-25 11:27
PTASK0050714 | Closed | AMS-AMO App Support Team-CN | 4 | 新CR上线的bug | zhang Song | 2019-01-30 14:46
PTASK0051487 | Closed | AMS-AMO App Support Team-CN | 4 | 目前AML没有清洗eclaim的数据 | Jonny Chang | 2019-02-20 16:39
PTASK0058067 | Closed | AMS-AMO App Support Team-CN | 4 | QAMTS调用手动任务方法异常出现Task的StartPeriod是2018年的，而EndPeriod时间是2013年，导致系统查询录音数据出现了程序处理不正常的数据的异常情况。 | zhang Haibo | 2019-08-06 18:01
PTASK0069138 | Closed | AMS-AMO App Support Team-CN | 4 | ED29AA_1主险份数输入框独有提示语切换到其他险种后不消失 | lan Lan | 2020-04-26 13:58
PTASK0049421 | Closed | AMS-AMO App Support Team-CN | 4 | imap应用升级临时策略方案 | lan Lan | 2018-12-24 16:42
PTASK0032579 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-01-25 10:24
PTASK0041310 | Closed | AMS-AMO App Support Team-CN | 3 | Identify Root Cause | zhang Song | 2018-06-07 13:55
PTASK0053241 | Closed | AMS-AMO App Support Team-CN | 4 | 自动化取号复用OldNew数据 针对新添加项目而未配置SEM限额数据 引起应用Job： AutoReuseOldNew的Exception 而影响整个全局功能 | zhang Haibo | 2019-04-03 14:04
PTASK0039126 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-04-27 15:21
PTASK0070115 | Closed | AMS-AMO App Support Team-CN | 4 | 资金平台扣款保单，缴费记录和非缴费记录显示错误 | Shutao Luo | 2020-05-20 15:38
PTASK0066294 | Closed | AMS-AMO App Support Team-CN | 4 | 自助理赔影像提交接口优化 | lan Lan | 2020-02-18 17:23
PTASK0057026 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Chen Cao | 2019-07-16 15:52
PTASK0060859 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-10-09 10:23
PTASK0038566 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Echo Yang | 2018-04-19 15:26
PTASK0038671 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-04-23 12:10
PTASK0062370 | Closed | AMS-AMO App Support Team-CN | 4 | 被保人手机号码填写的英文字母也能校验通过，只校验了手机号的前三位，会导致无法外呼。 | zhang Haibo | 2019-11-12 12:03
PTASK0046569 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-10-19 15:52
PTASK0043162 | Closed | AMS-AMO App Support Team-CN | 4 | 外点订单档上传时，遇到某保单信息有误时或异常时，即停止订单档中其他保单的导入，退出程序 | Jonny Lu | 2018-07-26 10:21
PTASK0055465 | Closed | AMS-AMO App Support Team-CN | 4 | 开发新上线的"付款清册"报表显示的交易笔数与实际出盘不符，通过PRB修改逻辑 | Li Chen | 2019-06-03 11:37
PTASK0050097 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-01-15 17:59
PTASK0050657 | Closed | AMS-AMO App Support Team-CN | 4 | 邮箱系统保单导入逻辑优化 | George Chan | 2019-01-29 15:55
PTASK0043633 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-08-07 15:53
PTASK0032859 | Closed | AMS-AMO App Support Team-CN | 2 | Identify Root Cause | Shutao Luo | 2018-01-30 11:32
PTASK0066064 | Closed | AMS-AMO App Support Team-CN | 4 | 自助理赔无法查询到客户信息 | lan Lan | 2020-02-13 15:17
PTASK0042632 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-07-12 17:09
PTASK0035353 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-05 14:04
PTASK0052088 | Closed | AMS-AMO App Support Team-CN | 4 | 报表添加会计年度 | Li Chen | 2019-03-07 14:43
PTASK0029072 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Haiyan Ren | 2017-11-27 10:33
PTASK0038335 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-04-17 10:53
PTASK0048078 | Closed | AMS-AMO App Support Team-CN | 4 | CCS推数耗时较长，开PRB持续跟进优化，预计结束时间2018/12/31 | Porter Deng | 2018-11-21 10:12
PTASK0057372 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-07-24 13:58
PTASK0054847 | Closed | AMS-AMO App Support Team-CN | 4 | 开发新上线存储过程删除了原逻辑中的一个条件， 导致该SP上线之后一直没有跑成功，该报表8号以后再没有数据。 | Li Chen | 2019-05-15 13:59
PTASK0052585 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Junhao Hu | 2019-03-19 10:23
PTASK0069809 | Closed | AMS-AMO App Support Team-CN | 4 | 代理人空中签名时，在投保书签字页面进行代理人签字时，CA加签异常（图片没有正常加签到PDF上） | Pengfei Wang | 2020-05-13 10:31
PTASK0058747 | Closed | AMS-AMO App Support Team-CN | 4 | 搜索问题 | zhang Song | 2019-08-20 12:03
PTASK0049770 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Yaoping Yaoping | 2019-01-07 11:30
PTASK0043223 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-07-27 15:13
PTASK0051877 | Closed | AMS-AMO App Support Team-CN | 4 | 智能核保动态问题12，13传值错误优化 | lan Lan | 2019-03-01 14:20
PTASK0055909 | Closed | AMS-AMO App Support Team-CN | 4 | 微信变更免密支付，由于代码问题，导致传入腾讯签约接口参数有问题，从而出现无法签约的情况 | Yaoping Yaoping | 2019-06-14 09:43
PTASK0044544 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-08-31 14:25
PTASK0041221 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-06-06 08:44
PTASK0051307 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-02-14 18:48
PTASK0043966 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-08-16 18:28
PTASK0069882 | Closed | AMS-AMO App Support Team-CN | 4 | 保单01049049保单在VMS里地址都是通讯地址（客户通讯地址和居住地址不一样），但是E-notice上传到供应商那里变成居住地址了，原因是什么?请查询具体原因，谢谢。 | Jonny Chang | 2020-05-14 14:46
PTASK0053239 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-04-03 11:20
PTASK0067535 | Closed | AMS-AMO App Support Team-CN | 4 | 使用客户五要素查询保单，发现有相同保单号的重复记录。 | Andy Chen | 2020-03-16 14:12
PTASK0044598 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | leo Luo | 2018-09-03 17:57
PTASK0041846 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-06-20 13:20
PTASK0053796 | Closed | AMS-AMO App Support Team-CN | 4 | 建议书加签报0kb提示，代理人重新加签无效 | lan Lan | 2019-04-16 09:35
PTASK0052828 | Closed | AMS-AMO App Support Team-CN | 4 | 微信提交理赔申请的时候,证件有效期为"1980-01-01" | zhang Song | 2019-03-25 15:54
PTASK0028406 | Closed | AMS-AMO Release Team-CN | 4 | 在BO报表系统中抽取的TM反洗钱保单证件未提交清单发现问题，保单的客户在清单中都显示证件已提交，但证件是否全部提交字段中仍显示为"否"，还请帮忙查看下原因。 | Terry Li | 2017-11-14 15:17
PTASK0064894 | Closed | AMS-AMO App Support Team-CN | 4 | 开发新上线 P3现金流拆分报表有重复数据，增量逻辑有缺陷，需修复 | Li Chen | 2020-01-15 11:33
PTASK0044735 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-09-06 13:19
PTASK0054106 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-04-24 16:20
PTASK0046919 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-10-26 15:15
PTASK0060793 | Closed | AMS-AMO App Support Team-CN | 4 | 电子合同申请兼容性问题无法正常下载 | zhang Song | 2019-10-08 15:19
PTASK0064601 | Closed | AMS-AMO App Support Team-CN | 4 | 四川民生项目订单档保单提交发送LA时，报错导致保单无法受理，提示："发送失败重复客户，请稍后再试！"？ | zhang Haibo | 2020-01-07 10:25
PTASK0036238 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-03-16 16:33
PTASK0043008 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-07-23 18:23
PTASK0047830 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2018-11-15 15:27
PTASK0046987 | Closed | AMS-AMO App Support Team-CN | 4 | 黑名单缺少查询条件判断 | zhang Song | 2018-10-29 12:10
PTASK0052833 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-03-25 17:41
PTASK0045705 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-09-29 14:34
PTASK0042990 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-07-23 11:50
PTASK0070591 | Closed | AMS-AMO App Support Team-CN | 4 | 由于外呼记录表数据将持续增长,目前根据附件截图的条件提取出脚本在数据库执行花费32秒时间，查询时间变长 | zhang Haibo | 2020-06-01 18:03
PTASK0041157 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2018-06-05 15:34
PTASK0057656 | Closed | AMS-AMO App Support Team-CN | 4 | 客户李敏，身份证号码340821198411012410，联系电话：18611343445 客户来电表示自己点击"0"积分兑换后，弹出"您的用户信息已被其他用户在都会堂注册"，无法进入到相关界面 | zhang Song | 2019-07-31 10:29
PTASK0036011 | Closed | AMS-AMO App Support Team-CN | 4 | 登录密码含有特殊字符时报错 |  | 2018-03-14 10:54
PTASK0053507 | Closed | AMS-AMO App Support Team-CN | 4 | 天津服务确认书，CA认证过程中，加签失败 | lan Lan | 2019-04-09 10:02
PTASK0045134 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-09-17 16:39
PTASK0046841 | Closed | AMS-AMO App Support Team-CN | 4 | 都会堂服务器空间满，造成图片加载不 出来 | leo Luo | 2018-10-25 17:24
PTASK0067854 | Closed | AMS-AMO App Support Team-CN | 4 | 身故受益人变更关系为其他时，在确认书上生成的文字内容与BRD不符 | lan Lan | 2020-03-23 11:00
PTASK0030906 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2017-12-26 14:53
PTASK0058471 | Closed | AMS-AMO App Support Team-CN | 4 | Reporting Agency明细表主键不严谨，导致数据业务上重复 | Porter Deng | 2019-08-13 18:01
PTASK0044254 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-08-24 14:05
PTASK0036007 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-14 09:33
PTASK0049477 | Closed | AMS-AMO App Support Team-CN | 4 | 提示书影像偶发遮盖 | lan Lan | 2018-12-26 13:16
PTASK0045639 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-09-28 14:23
PTASK0035034 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-02-28 18:06
PTASK0049877 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2019-01-09 16:15
PTASK0043955 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-08-16 11:59
PTASK0056189 | Closed | AMS-AMO App Support Team-CN | 4 | 解决CardPolicyJob的Exception问题 | zhang Haibo | 2019-06-21 16:54
PTASK0040804 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2018-05-25 16:35
PTASK0056170 | Closed | AMS-AMO App Support Team-CN | 4 | ECLAIM理赔明细表字段长度不够导致程序报错 | Shutao Luo | 2019-06-21 11:43
PTASK0054040 | Closed | AMS-AMO App Support Team-CN | 4 | 重庆人身投保提示书上日期有误， | lan Lan | 2019-04-23 14:44
PTASK0047738 | Closed | AMS-AMO App Support Team-CN | 4 | 手机号提取清洗 | Yaoping Yaoping | 2018-11-14 09:49
PTASK0035128 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2018-03-01 14:24
PTASK0054464 | Closed | AMS-AMO App Support Team-CN | 4 | BO报表未做加佣标识保单 | Shutao Luo | 2019-05-06 11:36
PTASK0051478 | Closed | AMS-AMO App Support Team-CN | 4 | 缴费记录增量数据较大导致ods 模型超时 | Shutao Luo | 2019-02-20 11:23
PTASK0043221 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-07-27 13:43
PTASK0038338 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jackie Cao | 2018-04-17 11:45
PTASK0045130 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause |  | 2018-09-17 14:28
PTASK0044096 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-08-21 14:40
PTASK0051989 | Closed | AMS-AMO App Support Team-CN | 4 | 投保书流程中电子保单查询页面，替换https://icare-cx.metlife.com.cn链接显示 | lan Lan | 2019-03-05 15:34
PTASK0049961 | Closed | AMS-AMO App Support Team-CN | 4 | 分公司通过理赔系统填报理赔申请时，如果E-CLAIM后台与bizflow服务器交互失败，E-CLAIM是不会提醒用户报错信息，但会造成bizflow整个Process信息是丢失。 | Jonny Chang | 2019-01-10 16:18
PTASK0057379 | Closed | AMS-AMO App Support Team-CN | 4 | 增加推送ENOTICE历史表的写入代码并修复CDR客户归并号增量同步问题 | Shutao Luo | 2019-07-24 15:37
PTASK0067914 | Closed | AMS-AMO App Support Team-CN | 4 | 保全查询结果无法在IOS13无法正常渲染 | Pengfei Wang | 2020-03-24 16:09
PTASK0061400 | Closed | AMS-AMO App Support Team-CN | 4 | ODS推数代理人信息到 CCS系统 增量控制有瑕疵 | Shutao Luo | 2019-10-22 18:32
PTASK0032018 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-01-16 11:57
PTASK0057203 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-07-19 14:00
PTASK0048577 | Closed | AMS-AMO App Support Team-CN | 4 | 投保单部分单证影像缺失 | lan Lan | 2018-12-03 15:18
PTASK0047836 | Closed | AMS-AMO App Support Team-CN | 4 | IMAP系统进入后会弹出信息提示"你有XX张保单受理超过10天"，点击查看，系统就死机，没有任何反映，点任何按钮都不行，需要强退。 | lan Lan | 2018-11-15 17:43
PTASK0055382 | Closed | AMS-AMO App Support Team-CN | 4 | （银联支付授权帐户与续期授权帐户一致）此项勾选后，银联支付授权帐户号码和授权帐户号码不一致。 | lan Lan | 2019-05-30 17:56
PTASK0057913 | Closed | AMS-AMO App Support Team-CN | 4 | 回签确认结果同步Pass系统之后的回写数据更新脚本报超时异常，出现的情况是： Update更新失败，系统会反复同步IVR 。 | zhang Haibo | 2019-08-02 16:40
PTASK0048631 | Closed | AMS-AMO App Support Team-CN | 4 | 打印系统分发给电子邮箱系统的保单确实文件 | Junhao Hu | 2018-12-04 17:03
PTASK0042073 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-06-26 16:55
PTASK0063516 | Closed | AMS-AMO App Support Team-CN | 4 | 身故受益人变更，选择受益人关系为法定，传入LA的关系为父母 | zhang Song | 2019-12-06 17:24
PTASK0055182 | Closed | AMS-AMO App Support Team-CN | 4 | 智能核保产品基本告知补充告知未填写也能保存成功，没有校验 | lan Lan | 2019-05-23 16:25
PTASK0056466 | Closed | AMS-AMO App Support Team-CN | 4 | 兴业外点系统发名单因系统超时报错，导致目前该专案名单被锁 | zhang Haibo | 2019-07-01 16:53
PTASK0050715 | Closed | AMS-AMO App Support Team-CN | 4 | 新产品上线，电销模板未修改造成建议书演示失败 | zhang Song | 2019-01-30 14:54
PTASK0044829 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-09-10 11:53
PTASK0036474 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-03-20 16:49
PTASK0040088 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-05-14 17:58
PTASK0046130 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-10-10 11:06
PTASK0056407 | Closed | AMS-AMO App Support Team-CN | 4 | 保单号：00439529，CCS端显示的保费和LA不一致，导致在线银联扣款无法操作（IVR界面不可以手动修改保费），实际保费应为318元 | Porter Deng | 2019-06-28 14:14
PTASK0033579 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-02-09 10:04
PTASK0039014 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-04-26 11:26
PTASK0048179 | Closed | AMS-AMO App Support Team-CN | 4 | SAP BO系统数据同步程序从Data Service迁移到Informatica， 统一调度，提升性能，便于管理与维护 | Li Chen | 2018-11-23 10:05
PTASK0045289 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-09-20 11:35
PTASK0054275 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-04-29 10:56
PTASK0038356 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-04-17 16:59
PTASK0042742 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-07-16 17:29
PTASK0048726 | Closed | AMS-AMO App Support Team-CN | 4 | PF143影像上传接口异常处理优化 | lan Lan | 2018-12-06 14:37
PTASK0035225 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-02 10:28
PTASK0055613 | Closed | AMS-AMO App Support Team-CN | 4 | 绑定提交时偶尔会出现系统维护中页面 | Yaoping Yaoping | 2019-06-06 09:58
PTASK0044833 | Closed | AMS-AMO App Support Team-CN | 4 | 从ODS同步到核心LA时增量推送逻辑有瑕疵 | Shutao Luo | 2018-09-10 14:31
PTASK0051878 | Closed | AMS-AMO App Support Team-CN | 4 | 关于承保客户带入非经营投保居住地址问题增加提示话术优化 | lan Lan | 2019-03-01 14:26
PTASK0026084 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2017-10-10 16:43
PTASK0064803 | Closed | AMS-AMO App Support Team-CN | 4 | 1月8日BO投连报表数据异常，经排查发现为BO_LA_VPRCPF_FIN表数据为空， 请ODS修改推数程序并修复数据 | Porter Deng | 2020-01-13 13:57
PTASK0044669 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-09-05 09:38
PTASK0046622 | Closed | AMS-AMO App Support Team-CN | 4 | 结案清单导出两条相同的新增附加险的保全 | zhang Song | 2018-10-22 15:49
PTASK0051546 | Closed | AMS-AMO App Support Team-CN | 4 | Pass传给E-Notice的批单数据中，同一批保单号不能重复，否则会导致生成XML报错。 | zhang Song | 2019-02-21 11:06
PTASK0056006 | Closed | AMS-AMO App Support Team-CN | 4 | 由于之前开发上了一个关于安全的需求,导致跑批程序通过域名访问官微webapi请求不到,而从保全积分未发送 | Yaoping Yaoping | 2019-06-18 15:38
PTASK0042122 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-06-27 10:07
PTASK0048857 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2018-12-10 12:58
PTASK0061458 | Closed | AMS-AMO App Support Team-CN | 4 | MTS系统薪资脚本优化问题 | Cylee Cao | 2019-10-23 15:02
PTASK0056287 | Closed | AMS-AMO App Support Team-CN | 4 | 续期催缴工单无法正常生成 | zhang Haibo | 2019-06-25 16:34
PTASK0049660 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-01-03 17:50
PTASK0050211 | Closed | AMS-AMO App Support Team-CN | 4 | circ系统年华保费产品明细报表功能有问题，用户下载报表内容有误 | Junhao Hu | 2019-01-17 17:51
PTASK0044831 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-09-10 13:56
PTASK0048919 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-12-11 14:44
PTASK0039815 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-05-09 13:32
PTASK0046689 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-10-23 11:45
PTASK0062719 | Closed | AMS-AMO App Support Team-CN | 4 | CIRC系统-"退保数据提取"模块为统计退保金相关报表，退保金数据与SUN财务账上的退保金数据不一致，请协助核对退保报表的取数逻辑，并修正报表取数逻辑，保证退保报表上的退保金与财务账上的退保金数一致。请见附件问题沟通邮件。 | Kevin Li | 2019-11-19 10:22
PTASK0050767 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | leo Luo | 2019-01-31 15:00
PTASK0060975 | Closed | AMS-AMO App Support Team-CN | 4 | enotice 生成xml 模板中没有配置相应数据 | zhang Song | 2019-10-11 11:09
PTASK0056567 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-07-03 11:40
PTASK0054640 | Closed | AMS-AMO App Support Team-CN | 4 | 因ADOBE自动升级导致打印终审闪退 | Chen Cao | 2019-05-09 17:37
PTASK0058940 | Closed | AMS-AMO App Support Team-CN | 4 | 保单41559959 8月份理赔金额为-15万，BO报表在逻辑上取了绝对值，所以显示 15万。 经与LA确认，理赔金额有可能为负数，用于冲账，所以应去除绝对值的逻辑 | Li Chen | 2019-08-26 10:17
PTASK0061288 | Closed | AMS-AMO App Support Team-CN | 4 | CDR 数据库中AM_FREE_CVRG表 ACTRISKCODE 字段长度为 20 ， ODS推往CDR的免费险数据被系统自动截断，保单FP0085186706，共有4个险种，只显示了3个。需扩展CDR数据库字段和修改推数程序 | Li Chen | 2019-10-18 17:20
PTASK0061239 | Closed | AMS-AMO App Support Team-CN | 4 | 未领清单月报（年报）报表 "营业网点/代理人编号/项目code" 字段 01 渠道， 代码备注写的是 代理人编号，取值却是 代理人姓名， 经与开发沟通， 确认取值有误，转PRB修复 | Li Chen | 2019-10-17 17:32
PTASK0049614 | Closed | AMS-AMO App Support Team-CN | 4 | ODS需要把每年1月1日的所有预估价格拦住，不推给下游系统 | Shutao Luo | 2019-01-02 17:28
PTASK0054584 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-05-08 17:57
PTASK0066937 | Closed | AMS-AMO App Support Team-CN | 4 | 优化投被保人证件照片由于网络原因导致的破损空白 | lan Lan | 2020-03-02 13:37
PTASK0042423 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-07-05 23:47
PTASK0035359 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-05 15:18
PTASK0041904 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-06-21 09:22
PTASK0048012 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-11-20 10:13
PTASK0050483 | Closed | AMS-AMO App Support Team-CN | 4 | CR1800826的广发月度薪酬数据开发BO 报表上生产后有一些小问题需调整 | Li Chen | 2019-01-24 14:39
PTASK0069139 | Closed | AMS-AMO App Support Team-CN | 4 | 保单贷款 兴业信用卡、招商信用卡、交行信用卡 进人工池 | zhang Song | 2020-04-26 17:48
PTASK0048022 | Closed | AMS-AMO App Support Team-CN | 4 | CIRC 部分保单数据重复 | Shutao Luo | 2018-11-20 16:08
PTASK0054039 | Closed | AMS-AMO App Support Team-CN | 4 | 增值服务计算套餐问题 | zhang Song | 2019-04-23 14:41
PTASK0052039 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-03-06 11:21
PTASK0055910 | Closed | AMS-AMO App Support Team-CN | 4 | 微信后台管理系统https://wechat.metlife.com.cn/weixinmanager/FAQ/Index—系统管理—Q&A维护—关键词报表。当前台同时搜索相同的关键词，后台报表出现一条搜索结果是"有"，一条结果是"无"的记录，两条记录显示搜索时间间隔3秒。4月初在链接功能上线前，经过测试（8个人同一时 | Yaoping Yaoping | 2019-06-14 09:53
PTASK0049882 | Closed | AMS-AMO App Support Team-CN | 4 | 开发上线时误加筛选器, 导致报表数据缺失，需移除筛选器 | Li Chen | 2019-01-09 17:51
PTASK0064023 | Closed | AMS-AMO App Support Team-CN | 4 | 核心数据异常机制优化 | Chen Cao | 2019-12-17 17:07
PTASK0048330 | Closed | AMS-AMO App Support Team-CN | 4 | 健告中被保人身高体重不能有小数优化 | lan Lan | 2018-11-28 17:02
PTASK0050424 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2019-01-23 14:37
PTASK0032748 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-01-29 11:50
PTASK0049057 | Closed | AMS-AMO App Support Team-CN | 4 | 投保单影像被保险人签名处被切割 | lan Lan | 2018-12-13 14:42
PTASK0034888 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause |  | 2018-02-27 17:51
PTASK0041224 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-06-06 11:57
PTASK0046921 | Closed | AMS-AMO App Support Team-CN | 4 | 1.历史VIP处理历史数据将历史数据修复。 2.增值服务有数据变化是由于bug造成前台查询不出数据和将level置空 | zhang Song | 2018-10-26 15:48
PTASK0049879 | Closed | AMS-AMO App Support Team-CN | 4 | LA ZCCTPF表中同一保单号 同一客户号 有多条记录，导致BO计算金额时数据翻倍 | Li Chen | 2019-01-09 16:56
PTASK0037814 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-04-10 17:47
PTASK0038494 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2018-04-18 16:26
PTASK0058394 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Chen Cao | 2019-08-12 14:50
PTASK0057797 | Closed | AMS-AMO App Support Team-CN | 4 | 从BO推到E-Notice续期通知表的缴清数据未作过滤 | Porter Deng | 2019-08-01 19:12
PTASK0063521 | Closed | AMS-AMO App Support Team-CN | 4 | ccs 红利明细报表展示领取方式和LA核心不一致 | Shutao Luo | 2019-12-06 19:50
PTASK0037931 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-04-11 10:22
PTASK0055027 | Closed | AMS-AMO App Support Team-CN | 4 | ODS模型部分代码还有调优空间，转成PROBLEM进行代码优化 | Shutao Luo | 2019-05-20 16:18
PTASK0050726 | Closed | AMS-AMO App Support Team-CN | 4 | pass手机号码16开头的验证不通过 | Yaoping Yaoping | 2019-01-30 20:21
PTASK0053652 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-04-11 16:11
PTASK0053144 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-04-01 15:51
PTASK0062731 | Closed | AMS-AMO App Support Team-CN | 4 | 如果建议书被保人与投被保人有家庭关系，且被保人为女性时，设置被保人时，被保人性别会被修改为默认值男性 | lan Lan | 2019-11-19 17:53
PTASK0067349 | Closed | AMS-AMO App Support Team-CN | 4 | 交叉销售业务下销售支持页面代码设计问题，打开网络加载框后，系统不会将这个加载框隐藏，导致无法继续操作。 | lan Lan | 2020-03-11 16:34
PTASK0036668 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-22 16:19
PTASK0053748 | Closed | AMS-AMO App Support Team-CN | 4 | 当投被保人非同一人，且证件已交附件为是，提交到filenet 时证件单证PM0281 重复，且文件内容都为被保人证件 | lan Lan | 2019-04-15 11:14
PTASK0054903 | Closed | AMS-AMO App Support Team-CN | 4 | 微保保单发送核心LA受理后，未生成推送微保的数据记录，最终导致承保的微保保单信息未能推送给微保系统 | Jonny Lu | 2019-05-16 09:48
PTASK0048077 | Closed | AMS-AMO App Support Team-CN | 4 | CCS扣款历史表数据有误 | Porter Deng | 2018-11-21 09:59
PTASK0044104 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-08-21 18:00
PTASK0055374 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Cylee Cao | 2019-05-30 11:35
PTASK0038492 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-04-18 16:20
PTASK0039990 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-05-11 14:20
PTASK0050478 | Closed | AMS-AMO App Support Team-CN | 4 | 投保单上投保人为特殊人群，收入来源说明显示有误 | lan Lan | 2019-01-24 10:17
PTASK0044963 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2018-09-12 14:36
PTASK0065008 | Closed | AMS-AMO App Support Team-CN | 4 | 代理人操作imap1.0会偶发编辑自己2.0系统里的保单 | lan Lan | 2020-01-17 11:30
PTASK0068121 | Closed | AMS-AMO App Support Team-CN | 4 | CCS系统调用MTS系统的 SurrenderPolicyService.asmx Web服务中的GenerateSurrenderTask 接口需要生成退保工单任务时失败了，提示："Transaction (Process ID 397) was deadlocked on lock resources wi | zhang Haibo | 2020-03-30 14:48
PTASK0050373 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Holly Cheng | 2019-01-22 17:20
PTASK0049054 | Closed | AMS-AMO App Support Team-CN | 4 | 在投被保人填写完毕后，填写受益人信息，首先勾选证件提交为Y，然后选择身份证，之后选择国籍后，OCR识别按钮置灰，无法点击。请帮忙修复。 | lan Lan | 2018-12-13 14:32
PTASK0049872 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-01-09 14:16
PTASK0042999 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-07-23 16:14
PTASK0056171 | Closed | AMS-AMO App Support Team-CN | 4 | 犹豫期内降保保单明细业绩报表 降保前ANP翻倍 | Shutao Luo | 2019-06-21 13:31
PTASK0053857 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Yaoping Yaoping | 2019-04-17 11:55
PTASK0035111 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause |  | 2018-03-01 09:53
PTASK0032654 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-01-26 09:32
PTASK0051224 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-02-12 20:41
PTASK0058109 | Closed | AMS-AMO App Support Team-CN | 4 | 应用系统JOB跑数据时，由于执行时间较长，跑到当天凌晨之后推送进入MTS的缴费数据，由于部分复效保单承保状态还未及时推送进入MTS或未复制分发到报表库，导致生成的实收保费记录被置为无效。 | zhang Haibo | 2019-08-07 11:28
PTASK0053433 | Closed | AMS-AMO App Support Team-CN | 4 | 该问题是由于获取工单任务时根据客户号获取状态最小的那一条任务；目前情况是，最新的任务是行销回收，该客户存在状态为行销回收的老任务，结果将老任务查询出来，获取任务专案中的外呼前缀，导致外呼失败。 | Jonny Lu | 2019-04-08 09:58
PTASK0038033 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-04-12 17:50
PTASK0029800 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2017-12-07 15:23
PTASK0026551 | Closed | AMS-AMO App Support Team-CN | 2 | Identify Root Cause | lan Lan | 2017-10-17 18:01
PTASK0047274 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Junhao Hu | 2018-11-05 14:31
PTASK0040858 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-05-28 17:36
PTASK0049325 | Closed | AMS-AMO App Support Team-CN | 4 | 打印2.70频繁宕机 | Junhao Hu | 2018-12-20 16:57
PTASK0049769 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Yaoping Yaoping | 2019-01-07 11:05
PTASK0055124 | Closed | AMS-AMO App Support Team-CN | 4 | E-NOTICE调用CDR接口返回NO DATA FOUND或者email、sms数据有问题 | George Chan | 2019-05-22 13:51
PTASK0049327 | Closed | AMS-AMO App Support Team-CN | 4 | E-NOTICE对于部分推送过来的批单数据会数据丢失。 | zhang Song | 2018-12-20 17:04
PTASK0032658 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-01-26 14:05
PTASK0040379 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2018-05-17 10:08
PTASK0048391 | Closed | AMS-AMO App Support Team-CN | 4 | 为保证ODS daily推数正常运行，避免因锁表等带来的不可预期的问题，准备添加KILL非ODS进程的程序 | Porter Deng | 2018-11-29 16:58
PTASK0049826 | Closed | AMS-AMO App Support Team-CN | 4 | ODS推PASS LCBANK报错，系LA银行名称配置缺失导致，经LA确认，银行名称允许为空，且下游反馈银行名称为空不影响业务，现调整ODS推数逻辑，提高系统容错性 | Porter Deng | 2019-01-08 17:26
PTASK0049771 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-01-07 12:12
PTASK0055698 | Closed | AMS-AMO App Support Team-CN | 4 | 逾期未付选项变更和交费频率变更这两个保全项的保单号是新保单号，而保单列表显示是旧保单单号，需要按照保单列表页面中显示的保单号为基准，前后统一显示 | Yaoping Yaoping | 2019-06-10 11:26
PTASK0059434 | Closed | AMS-AMO App Support Team-CN | 4 | 需签批含贷款案件，清算与结案时间不一致导致理赔金额不符，需要在签批岗重新调取清算接口。 | Jonny Chang | 2019-09-05 10:35
PTASK0056682 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-07-08 10:38
PTASK0046270 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-10-12 11:02
PTASK0036343 | Closed | AMS-AMO App Support Team-CN | 3 | Identify Root Cause | zhang Haibo | 2018-03-19 15:41
PTASK0055081 | Closed | AMS-AMO App Support Team-CN | 4 | 江苏省保协要求在"江苏省保险业销售服务评价系统"上传一年期以上产品的承保数据，现上传数据中包含一年期的医疗险和意外险，申请删除所有一年期产品。 | Andy Chen | 2019-05-21 10:08
PTASK0027584 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2017-11-01 14:39
PTASK0043050 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-07-24 10:40
PTASK0054152 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-04-25 14:38
PTASK0051303 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-02-14 14:16
PTASK0048285 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-11-27 18:44
PTASK0036670 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-22 17:00
PTASK0065058 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Chen Cao | 2020-01-20 16:01
PTASK0048578 | Closed | AMS-AMO App Support Team-CN | 4 | 孤儿单清单报表运行时间长，需优化 | Li Chen | 2018-12-03 15:55
PTASK0060203 | Closed | AMS-AMO App Support Team-CN | 4 | reporting 需要新增推送月结表数据 | Shutao Luo | 2019-09-24 19:04
PTASK0056618 | Closed | AMS-AMO App Support Team-CN | 4 | 2019年7月1日综合交付平台处理速度很慢，进检查后台日志，发现有四十多条线程hung住。 | Chen Cao | 2019-07-04 11:38
PTASK0064603 | Closed | AMS-AMO App Support Team-CN | 4 | MTS系统 报表>业绩统计类>犹豫期内降保保单明细业绩报表，降保前ANP与降保后ANP一致 | zhang Haibo | 2020-01-07 10:35
PTASK0067679 | Closed | AMS-AMO App Support Team-CN | 4 | Reporting系统 BCP下 扣款清册报表运行缓慢，进行优化 | Li Chen | 2020-03-18 10:28
PTASK0042067 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-06-26 12:00
PTASK0050428 | Closed | AMS-AMO App Support Team-CN | 4 | 三位TSR都提示："前一工作日有未完成的回拨任务" 是系统正常提示，确实有未完成的回拨任务，但任务都被转移给 TSR 刘金枝 工号958441。 | zhang Haibo | 2019-01-23 16:20
PTASK0030208 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2017-12-14 17:18
PTASK0044545 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-08-31 14:28
PTASK0048474 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-11-30 14:06
PTASK0047273 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-11-05 13:59
PTASK0042573 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-07-11 11:18
PTASK0059635 | Closed | AMS-AMO App Support Team-CN | 4 | 微保免险我们系统已取消，微保小程序依然还是显示保障中，烦请核查原因并处理，谢谢～ 团队反馈不止这一单，烦请尽快核查原因并处理，谢谢～ | Jonny Lu | 2019-09-10 11:52
PTASK0053965 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-04-19 16:28
PTASK0047675 | Closed | AMS-AMO App Support Team-CN | 4 | pass做续期账号变更时，保全取消的单子发往ENOTICE，造成enotice解析失败 | zhang Song | 2018-11-13 17:06
PTASK0033122 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-02-02 17:46
PTASK0058761 | Closed | AMS-AMO App Support Team-CN | 4 | 缴费频率变更bug | zhang Song | 2019-08-20 17:41
PTASK0044100 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-08-21 16:16
PTASK0067146 | Closed | AMS-AMO App Support Team-CN | 4 | 万能保险利息结算日公告页面chrome无法打开，兼容调优 | lan Lan | 2020-03-06 12:05
PTASK0035017 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-02-28 09:59
PTASK0059019 | Closed | AMS-AMO App Support Team-CN | 4 | MTS 的WebService：OnlineSales 中的接口 ReceiveResult （微信投保/短信投保的回签确认结果返回）接口有死锁问题 | zhang Haibo | 2019-08-27 17:38
PTASK0057331 | Closed | AMS-AMO App Support Team-CN | 4 | 从PASS推送回签时间到MTS逻辑有缺陷 | Porter Deng | 2019-07-23 18:27
PTASK0061361 | Closed | AMS-AMO App Support Team-CN | 3 | Identify Root Cause | Andy Chen | 2019-10-21 20:42
PTASK0060408 | Closed | AMS-AMO App Support Team-CN | 4 | mtsrpt-报表-回访任务报表-薪资报表-实收保费绩效明细报表-复效保单已经承保了，但在系统里没有体现出实收保费记录。 | zhang Haibo | 2019-09-27 17:57
PTASK0042739 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Echo Yang | 2018-07-16 15:42
PTASK0056357 | Closed | AMS-AMO App Support Team-CN | 4 | QAMTS调用手动任务方法异常，给时间添加年份后出现了ArgumentOutOfRangeException异常 | zhang Haibo | 2019-06-27 11:49
PTASK0038028 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-04-12 15:23
PTASK0043000 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-07-23 16:18
PTASK0048918 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Yaoping Yaoping | 2018-12-11 14:19
PTASK0066877 | Closed | AMS-AMO App Support Team-CN | 4 | 净承保汇总业绩清单运行的慢的脚本 | zhang Haibo | 2020-02-28 15:38
PTASK0031097 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jackie Cao | 2017-12-29 11:13
PTASK0033578 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-02-09 09:30
PTASK0060935 | Closed | AMS-AMO App Support Team-CN | 4 | TSR修改了地址，新契约处无法看见已修改的新地址，显示出来还是未修改过的地址，导致此单一直无法审核通过，烦请处理，谢谢！ | zhang Haibo | 2019-10-10 15:20
PTASK0064489 | Closed | AMS-AMO App Support Team-CN | 4 | 交清增额报表，本次红利分配后累计增加的保额 5977.00元，但报表显示7200元。 原因是开发新上线需求，新增字段 关联HPUAPF表时未过滤validflag <> 1 的数据， 导致PUA金额计算错误 | Li Chen | 2020-01-03 12:10
PTASK0068736 | Closed | AMS-AMO App Support Team-CN | 4 | imap1.0调整重置密码方式 | lan Lan | 2020-04-15 15:45
PTASK0035110 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-01 09:26
PTASK0048570 | Closed | AMS-AMO App Support Team-CN | 4 | CIRC跑数对ODS产生锁表 | Shutao Luo | 2018-12-03 11:17
PTASK0055804 | Closed | AMS-AMO App Support Team-CN | 4 | 同一保单出现两个被保人，导致无法保费计算 | Kevin Li | 2019-06-12 16:11
PTASK0038491 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause |  | 2018-04-18 16:18
PTASK0045237 | Closed | AMS-AMO App Support Team-CN | 3 | Identify Root Cause | zhang Song | 2018-09-19 11:33
PTASK0035575 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-07 17:20
PTASK0048015 | Closed | AMS-AMO App Support Team-CN | 4 | 添加邮件监控， 检测节假日期间投连报表每日金额是否一致 | Li Chen | 2018-11-20 10:43
PTASK0028494 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2017-11-15 14:15
PTASK0029707 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2017-12-06 15:08
PTASK0042450 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-07-06 11:37
PTASK0036661 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-03-22 13:11
PTASK0049878 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2019-01-09 16:17
PTASK0048466 | Closed | AMS-AMO App Support Team-CN | 4 | 调整comp佣金明细表推数逻辑（inbound ），全量推数性能缓慢影响OP跑批调度 | Porter Deng | 2018-11-30 11:27
PTASK0045131 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Junhao Hu | 2018-09-17 14:51
PTASK0068205 | Closed | AMS-AMO App Support Team-CN | 4 | 敏感信息权限 | George Chan | 2020-04-01 13:47
PTASK0057919 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2019-08-02 17:52
PTASK0059642 | Closed | AMS-AMO App Support Team-CN | 4 | SemInterface 接口 ImportCustomer中有更新客户资料的描述信息，后台数据库里定义的长度是1000个字符，当更新长度超过1000个字符时程序抛异常。 | zhang Haibo | 2019-09-10 17:38
PTASK0058689 | Closed | AMS-AMO App Support Team-CN | 4 | Daily Sales Report报表导出抛异常，语法错误异常无法查看报表。 | zhang Haibo | 2019-08-19 18:01
PTASK0070195 | Closed | AMS-AMO App Support Team-CN | 4 | 退保的保单不需要推送保单现价，目前LA并不做处理，需要ODS增加过滤条件，转PRB修复 | Shutao Luo | 2020-05-21 18:15
PTASK0063390 | Closed | AMS-AMO App Support Team-CN | 4 | 用户登录，权限问题 | George Chan | 2019-12-04 10:28
PTASK0033429 | Closed | AMS-AMO App Support Team-CN | 4 | B2B推送主副险逻辑修改 | Shutao Luo | 2018-02-07 16:57
PTASK0057918 | Closed | AMS-AMO App Support Team-CN | 4 | 官微同步pass数据无法更新 | zhang Song | 2019-08-02 17:37
PTASK0055919 | Closed | AMS-AMO App Support Team-CN | 4 | MTS中客户档案-资料维护页面加载或查询时，都会全量查询Calllist数据，导致查询较慢 | Jonny Lu | 2019-06-14 15:59
PTASK0069670 | Closed | AMS-AMO App Support Team-CN | 4 | pass 犹退校验规则添加中保信身份验证 | zhang Song | 2020-05-09 17:24
PTASK0059706 | Closed | AMS-AMO App Support Team-CN | 4 | VMS server OOM | leo Luo | 2019-09-11 14:12
PTASK0039129 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-04-27 15:45
PTASK0052268 | Closed | AMS-AMO App Support Team-CN | 4 | CIRC视图逻辑对共单保单统计重复 | Shutao Luo | 2019-03-12 11:44
PTASK0068595 | Closed | AMS-AMO App Support Team-CN | 4 | 理赔生成pdf 名字中有复杂的字无法显示 | zhang Song | 2020-04-13 14:51
PTASK0049125 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-12-14 18:24
PTASK0068061 | Closed | AMS-AMO App Support Team-CN | 4 | 外点MTS 通过重复点选可以实现手机号外显。 | zhang Haibo | 2020-03-27 09:26
PTASK0049955 | Closed | AMS-AMO App Support Team-CN | 4 | 湖北省鄂州市县级市地址编码错纠正 | lan Lan | 2019-01-10 13:48
PTASK0058601 | Closed | AMS-AMO App Support Team-CN | 4 | MTS系统的新契约使用的保单审核功能发送保单进LA核心系统出现提示：" TempPolicuNum + 发送失败重复客户，请稍后再试!" | zhang Haibo | 2019-08-15 15:44
PTASK0045132 | Closed | AMS-AMO App Support Team-CN | 4 | 打印系统2.70频繁宕机 | Junhao Hu | 2018-09-17 15:25
PTASK0047979 | Closed | AMS-AMO App Support Team-CN | 4 | 重庆武汉大连辽宁分公司某些流程会绕过OCR识别 | lan Lan | 2018-11-19 14:51
PTASK0039385 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-05-02 15:54
PTASK0060316 | Closed | AMS-AMO App Support Team-CN | 4 | 理赔明细报表计算金额时未乘正负标记，导致金额计算有误 | Li Chen | 2019-09-26 11:05
PTASK0041409 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-06-11 10:06
PTASK0055090 | Closed | AMS-AMO App Support Team-CN | 4 | Eclaim生成理赔通知书后，给到打印上传filenent缺失理赔报案号 | Chen Cao | 2019-05-21 18:21
PTASK0053586 | Closed | AMS-AMO App Support Team-CN | 4 | 加签重叠 | lan Lan | 2019-04-10 16:28
PTASK0047980 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2018-11-19 16:00
PTASK0033420 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-02-07 10:19
PTASK0042264 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-07-02 11:46
PTASK0054695 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Yaoping Yaoping | 2019-05-10 15:45
PTASK0038026 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jackie Cao | 2018-04-12 15:14
PTASK0050085 | Closed | AMS-AMO App Support Team-CN | 3 | BO 程序删除ETL_DATATYPE = 'D'的记录 | Shutao Luo | 2019-01-15 09:47
PTASK0038024 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-04-12 13:37
PTASK0046916 | Closed | AMS-AMO App Support Team-CN | 4 | 推数逻辑做调整，不需要的数据不需要推送给ECLAIM | Shutao Luo | 2018-10-26 13:50
PTASK0044675 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-09-05 12:07
PTASK0032406 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Echo Yang | 2018-01-23 15:13
PTASK0068262 | Closed | AMS-AMO App Support Team-CN | 4 | imap2.0前端回签和回访日期显示错位 | lan Lan | 2020-04-02 15:52
PTASK0053653 | Closed | AMS-AMO App Support Team-CN | 4 | AGY客户生日报表新上线的功能有逻辑问题 | Li Chen | 2019-04-11 16:20
PTASK0052827 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-03-25 15:43
PTASK0036242 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-03-16 16:59
PTASK0042995 | Closed | AMS-AMO App Support Team-CN | 4 | 招行网销（短险）当产品的保障期限的信息未配置的情况下，导入的订单档数据与该产品相关的数据无法导入系统，需要对程序做调整。 | zhang Haibo | 2018-07-23 15:21
PTASK0039024 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-04-26 15:34
PTASK0053798 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2019-04-16 11:18
PTASK0054100 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2019-04-24 13:55
PTASK0061502 | Closed | AMS-AMO App Support Team-CN | 4 | 投保过程特殊操作可以绕过身份证拍照流程导致证件空白 | lan Lan | 2019-10-24 09:32
PTASK0068500 | Closed | AMS-AMO App Support Team-CN | 4 | 复效黑名单校验 | zhang Song | 2020-04-09 15:12
PTASK0058470 | Closed | AMS-AMO App Support Team-CN | 4 | 用户要求 付款清册EBS报表 仅显示批量出回盘的数据，现报表逻辑与用户需求不符 | Li Chen | 2019-08-13 17:54
PTASK0033328 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-02-06 15:03
PTASK0043332 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Shutao Luo | 2018-07-31 10:06
PTASK0051880 | Closed | AMS-AMO App Support Team-CN | 4 | 自助理赔拍照图片清晰度优化 | lan Lan | 2019-03-01 15:21
PTASK0039640 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-05-07 17:20
PTASK0067864 | Closed | AMS-AMO App Support Team-CN | 4 | 24银保新单受理报表"投保单号、银行网点名称、银行名称"3个字段的数据值后存在大量空格，转PRB去空格 | Li Chen | 2020-03-23 16:54
PTASK0042453 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-07-06 15:53
PTASK0047740 | Closed | AMS-AMO App Support Team-CN | 4 | ANP汇总报表逻辑中的union，将同一天承保又退保再重新承保的相同保额的数据进行了去重，导致ANP总和不对 | Li Chen | 2018-11-14 10:14
PTASK0064288 | Closed | AMS-AMO App Support Team-CN | 4 | BO报表"6-银行自动转账失败通知单" PAYRPF表关联时未过滤ETL_DATATYPE = D 的数据， 导致数据重复， 金额翻倍。 | Li Chen | 2019-12-25 10:44
PTASK0061858 | Closed | AMS-AMO App Support Team-CN | 4 | MTS系统保单表里的LastFailReason值是ODS推送给MTS的 ；其中含有特殊字符导致MTS查询时在前端页面查询会有报错，麻烦ODS同事推送数据时处理掉特殊字符。 | Porter Deng | 2019-10-31 10:46
PTASK0037813 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-04-10 17:46
PTASK0029074 | Closed | AMS-AMO App Support Team-CN | 4 | 修改MTS保单审核页面证件类型为"返乡证" | Jonny Lu | 2017-11-27 12:03
PTASK0038360 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-04-17 17:35
PTASK0059265 | Closed | AMS-AMO App Support Team-CN | 4 | 新一站项目提出承保报错，并多次出现，请协助处理，附件为报错提示。 | zhang Haibo | 2019-09-03 11:23
PTASK0049152 | Closed | AMS-AMO App Support Team-CN | 4 | CIRIC从ODS取主副险标识判断逻辑有错误 | Shutao Luo | 2018-12-17 13:20
PTASK0050091 | Closed | AMS-AMO App Support Team-CN | 4 | 客诉反映其保单01807245红利信函收到后发现信函上数据与实际不符 经调查发现增额红利数据至Enotice上线以来的取值全部有误，受影响保单122件（短信：97，纸质：25） | zhang Song | 2019-01-15 16:22
PTASK0049123 | Closed | AMS-AMO App Support Team-CN | 4 | 智能核保问题修复，被保人年龄小于二岁时，基本告知页，少儿告知不能点击'否' | lan Lan | 2018-12-14 17:53
PTASK0046024 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Holly Cheng | 2018-10-08 14:31
PTASK0049876 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2019-01-09 16:13
PTASK0047173 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-11-01 20:08
PTASK0057257 | Closed | AMS-AMO App Support Team-CN | 2 | Identify Root Cause | Chen Cao | 2019-07-20 12:40
PTASK0035246 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2018-03-02 17:04
PTASK0070587 | Closed | AMS-AMO App Support Team-CN | 4 | MTS应用Job：EmployeeSuperviseCondition 执行异常，提示："Invalid object name 'AP_P_PersonBase" | zhang Haibo | 2020-06-01 17:46
PTASK0053137 | Closed | AMS-AMO App Support Team-CN | 4 | 逻辑中不含网销，导致 "核保未回复明细报表"、"TM反洗钱保单证件未提交清单"中网销渠道保单"区部/组字段"信息显示为空 | Li Chen | 2019-04-01 10:09
PTASK0041160 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-06-05 15:58
PTASK0047049 | Closed | AMS-AMO App Support Team-CN | 4 | 目前推数MAP_LJAPAY的逻辑写在视图里，当数据量较大时视图查询过慢，导致推数缓慢，MAP和CCS数据库在同一台物理机，MAP推数慢也会影响CCS推数，所以需要调优 | Shutao Luo | 2018-10-30 11:12
PTASK0053242 | Closed | AMS-AMO App Support Team-CN | 4 | 京东数据的入库应用Job： ImportJDSDCustomer 调整频率由现在每天早8点调整为10点钟执行。 | zhang Haibo | 2019-04-03 15:03
PTASK0043765 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-08-10 11:41
PTASK0060097 | Closed | AMS-AMO App Support Team-CN | 4 | Reporting CSO登录页面公司名称显示错误 | lan Lan | 2019-09-20 13:46
PTASK0068602 | Closed | AMS-AMO App Support Team-CN | 4 | 未成年人户口本有效期根据出生日期计算逻辑与map不破配 | lan Lan | 2020-04-13 17:16
PTASK0054793 | Closed | AMS-AMO App Support Team-CN | 4 | PASS日常批单数据推送到E-NOTICE后，E-NOTICE在处理过程中有部分数据缺失，两边数据对不上。 | zhang Song | 2019-05-14 10:52
PTASK0061170 | Closed | AMS-AMO App Support Team-CN | 4 | Wehcat_pfm推数结束时间超过RPIS和EZT系统同步数据时间，RPIS和EZT只能同步部分数据，RPIS的数据中心报表数据和EZT的目标管理中的达成数据不全，需ODS优化推数逻辑 | Porter Deng | 2019-10-16 15:23
PTASK0054848 | Closed | AMS-AMO App Support Team-CN | 4 | 打印系统等待分发列表数据量一旦超过一定的阀值，会导致打印分发处理失败 | Chen Cao | 2019-05-15 15:34
PTASK0053198 | Closed | AMS-AMO App Support Team-CN | 4 | 00250925,客户在微信端只申请了 通讯地址变更，但是在PASS端生成了两个保全变更业务 T123¦客户电话/邮箱变更 T102¦通讯地址及邮编变更 烦请查询原因，谢谢 | Yaoping Yaoping | 2019-04-02 11:34
PTASK0048213 | Closed | AMS-AMO App Support Team-CN | 4 | 投保书遮盖问题 | lan Lan | 2018-11-26 11:19
PTASK0069212 | Closed | AMS-AMO App Support Team-CN | 4 | vip，zyh ，产品增值服务案件录入导出问题 | zhang Song | 2020-04-28 15:50
PTASK0043159 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-07-26 09:48
PTASK0056579 | Closed | AMS-AMO App Support Team-CN | 4 | 红利数据缺失 | zhang Song | 2019-07-03 18:23
PTASK0061341 | Closed | AMS-AMO App Support Team-CN | 4 | 短信验证重发按钮与语音验证不显示问题 | lan Lan | 2019-10-21 13:50
PTASK0033039 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-02-01 13:38
PTASK0044372 | Closed | AMS-AMO App Support Team-CN | 3 | Identify Root Cause | Kevin Li | 2018-08-28 14:17
PTASK0057582 | Closed | AMS-AMO App Support Team-CN | 4 | VIP 数据延迟调整 | zhang Song | 2019-07-30 09:56
PTASK0051597 | Closed | AMS-AMO App Support Team-CN | 4 | 年度应用证书更新 | lan Lan | 2019-02-22 16:15
PTASK0035897 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Porter Deng | 2018-03-13 13:24
PTASK0039823 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-05-09 18:00
PTASK0041460 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-06-12 10:44
PTASK0055250 | Closed | AMS-AMO App Support Team-CN | 4 | ECLAIM（理赔数据）同步到CDR的代码有缺陷，需要转成problem修复 | Shutao Luo | 2019-05-27 14:19
PTASK0059383 | Closed | AMS-AMO App Support Team-CN | 4 | ITEMPF 表 同一个 ITEM 对应了 2 个 COMPANY，导致金额翻倍， 经与LA确认， COMPANY=0 为无效数据，因此需要修改存储过程逻辑，过滤掉无效数据。 | Li Chen | 2019-09-04 15:14
PTASK0048013 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-11-20 10:14
PTASK0040625 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-05-22 17:32
PTASK0057584 | Closed | AMS-AMO App Support Team-CN | 4 | CHDRPF表缺少TRANNO = 2000的历史数据 | Porter Deng | 2019-07-30 11:25
PTASK0058951 | Closed | AMS-AMO App Support Team-CN | 4 | 系统生成的团险被保险人个人凭证中，当某一单元格内字符较多需要换行时，表格中会多出一条横线且与下方内容重叠。 | Chen Cao | 2019-08-26 14:09
PTASK0051820 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-02-28 11:52
PTASK0048281 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-11-27 17:33
PTASK0061932 | Closed | AMS-AMO App Support Team-CN | 4 | 团险交叉销售保单无法显示第一页之后的查询结果数据 | lan Lan | 2019-11-01 14:33
PTASK0049814 | Closed | AMS-AMO App Support Team-CN | 4 | 报表《未领清单（退保/满期）月报表》和《未领清单（退保/满期）年报表》中保单00510369显示累计待领金额5000元。但保单实际无待领金额。请核实问题。 | Porter Deng | 2019-01-08 10:34
PTASK0045293 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2018-09-20 15:34
PTASK0058757 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-08-20 17:05
PTASK0042994 | Closed | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Li Chen | 2018-07-23 14:41
PTASK0057015 | Closed | AMS-AMO App Support Team-CN | 4 | IBM监控打印后台日志，捕捉到部分sql非常占用CPU，需要进行改造。 | Chen Cao | 2019-07-16 14:22
PTASK0056568 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Andy Chen | 2019-07-03 13:44
PTASK0038027 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-04-12 15:15
PTASK0031913 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-01-12 16:42
PTASK0057019 | Cancelled | AMS-AMO App Support Team-CN | 4 | 智能核保告知问卷答案错位 | lan Lan | 2019-07-16 15:11
PTASK0034868 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-02-27 15:23
PTASK0026085 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2017-10-10 16:48
PTASK0053651 | Cancelled | AMS-AMO App Support Team-CN | 4 | PASS日常批单数据推送到E-NOTICE后，E-NOTICE在处理过程中有部分数据缺失，两边数据对不上。 | zhang Song | 2019-04-11 16:01
PTASK0027253 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2017-10-26 14:14
PTASK0027495 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2017-10-31 16:37
PTASK0029073 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2017-11-27 11:07
PTASK0061810 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-10-30 16:01
PTASK0031891 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause |  | 2018-01-12 10:27
PTASK0051553 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-02-21 15:49
PTASK0054105 | Cancelled | AMS-AMO App Support Team-CN | 4 | 投被保人、受益人证件，投被保人活体识别照片空白 | lan Lan | 2019-04-24 16:14
PTASK0064615 | Cancelled | AMS-AMO App Support Team-CN | 4 | 兼容性问题 | zhang Song | 2020-01-07 17:00
PTASK0049076 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-12-13 17:58
PTASK0044490 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2018-08-30 17:42
PTASK0032016 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-01-16 10:53
PTASK0037695 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-04-08 17:48
PTASK0057993 | Cancelled | AMS-AMO App Support Team-CN | 4 | 提数设计过于冗余，提数脚本重复执行导致执行时间翻倍 | Echo Yang | 2019-08-05 16:26
PTASK0034722 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause |  | 2018-02-26 17:50
PTASK0056412 | Cancelled | AMS-AMO App Support Team-CN | 4 | 周六OldNew和每天非工作时间段实时数据复用使用的标签打分表未创建导致的程序执行异常问题 | zhang Haibo | 2019-06-28 17:21
PTASK0026905 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2017-10-23 16:42
PTASK0069814 | Cancelled | AMS-AMO App Support Team-CN | 4 | 026000005607投保变更通知书排版有误，打印文字重叠，请处理. 保险计划这一块内容字体改为9号的显示效果，原来是宋体10号，无其他变动。 | Chen Cao | 2020-05-13 13:39
PTASK0028684 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2017-11-17 16:36
PTASK0030115 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Kevin Li | 2017-12-13 11:00
PTASK0058800 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-08-21 10:45
PTASK0035558 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-03-07 09:59
PTASK0032870 | Cancelled | AMS-AMO App Support Team-CN | 2 | Identify Root Cause | Porter Deng | 2018-01-30 15:58
PTASK0055911 | Cancelled | AMS-AMO App Support Team-CN | 4 | 扣款清册报表"期次"字段逻辑有误，导致保费的期次计算比LA少一期 | Li Chen | 2019-06-14 10:11
PTASK0060199 | Cancelled | AMS-AMO App Support Team-CN | 4 | 生成回访不成功扣款追踪工单有异常 | zhang Haibo | 2019-09-24 16:51
PTASK0029421 | Cancelled | AMS-AMO App Support Team-CN | 4 | SMIS-在系统中增加2018财年 | Jonny Lu | 2017-12-01 09:57
PTASK0051588 | Cancelled | AMS-AMO App Support Team-CN | 4 | 身份证号码校验失败，需要修改校验逻辑 | Yaoping Yaoping | 2019-02-22 09:45
PTASK0026155 | Cancelled | AMS-AMO App Support Team-CN | 2 | Identify Root Cause | lan Lan | 2017-10-11 14:08
PTASK0069137 | Cancelled | AMS-AMO App Support Team-CN | 4 | 户口本身份证号证件有效期计算错误 | lan Lan | 2020-04-26 13:43
PTASK0059015 | Cancelled | AMS-AMO App Support Team-CN | 4 | 短信发送重复， 该问题是由于短信JOB执行时，服务器停止导致未能将发送成功的短信置上已发送标识，第二天执行JOB再次将短信发送短信平台。 | zhang Haibo | 2019-08-27 17:04
PTASK0056283 | Cancelled | AMS-AMO App Support Team-CN | 4 | http://rpt.metlife.cn/reporting/ 湖北顾问行销渠道从该Reporting系统中下载业绩报表，发现保单号071000006135的保单，在运营处查询该保单保费为7791元，且是年缴保单，未做过任何变更 | Porter Deng | 2019-06-25 14:23
PTASK0038351 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-04-17 14:17
PTASK0047976 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-11-19 11:32
PTASK0026663 | Cancelled | AMS-AMO App Support Team-CN | 2 | Identify Root Cause | zhang Haibo | 2017-10-18 17:16
PTASK0035018 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-02-28 10:08
PTASK0050311 | Cancelled | AMS-AMO App Support Team-CN | 4 | 由于在代码bug 。复效时，将微信免密的银行帐号删除 | Yaoping Yaoping | 2019-01-21 13:10
PTASK0046384 | Cancelled | AMS-AMO App Support Team-CN | 4 | 分公司导出结案清单和未结案清单由于数据量比较大查询时间过长需要优化数据 | zhang Song | 2018-10-16 14:59
PTASK0051308 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-02-14 19:28
PTASK0035233 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-03-02 15:26
PTASK0035565 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2018-03-07 15:52
PTASK0037038 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2018-03-28 10:02
PTASK0063864 | Cancelled | AMS-AMO App Support Team-CN | 4 | 保单对应的投被保人信息中的CompanyName"公司名称"字段超长，因与核心LA系统定义字段长度不同，导致保单在发送LA系统时报异常，无法正常同步 | Cylee Cao | 2019-12-12 14:53
PTASK0058760 | Cancelled | AMS-AMO App Support Team-CN | 4 | 03614201 这个保单的被保险人，曹冰宜 7.22 申请了证件止期变更，且已变更成功，但是在PASS 页面，这个保单的当前证件止期对应的影像标示： N，烦请确认原因，因在需求中说明，只要调用T215的保全变更，Pass中的当前证件止期对应的影像标示会更新为 Y | zhang Song | 2019-08-20 17:30
PTASK0056957 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2019-07-15 17:05
PTASK0054038 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Song | 2019-04-23 14:11
PTASK0031164 | Cancelled | AMS-AMO App Support Team-CN | 2 | Identify Root Cause | lan Lan | 2018-01-02 09:52
PTASK0035796 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-03-12 14:07
PTASK0055526 | Cancelled | AMS-AMO App Support Team-CN | 4 | AutoReuseOldNew 自动任务在 2019-05-04～2019-05-20三周出现未正常复用信息流数据的情况。 | zhang Haibo | 2019-06-04 16:59
PTASK0061741 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-10-29 15:28
PTASK0030739 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | lan Lan | 2017-12-21 14:43
PTASK0047597 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | Jonny Lu | 2018-11-12 13:58
PTASK0034859 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause |  | 2018-02-27 11:06
PTASK0052346 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | zhang Haibo | 2019-03-13 16:05
PTASK0067152 | Cancelled | AMS-AMO App Support Team-CN | 4 | CMSCallhistory 没有相应的Task即拨打任务，无法下发数据。 | zhang Haibo | 2020-03-06 15:07
PTASK0031893 | Cancelled | AMS-AMO App Support Team-CN | 4 | Identify Root Cause | George Chan | 2018-01-12 10:37
PTASK0058893 | Cancelled | AMS-AMO App Support Team-CN | 4 | TSR取号量 报表查询慢无法反馈查询结果到页面上。 | zhang Haibo | 2019-08-23 16:12